## Tasks
WBS Number | Task name / Title | Assigned to | Planned start time | Planned end time | Depends (predecessors) | Duration (days)
WBS Number | Software Development Project | ALL | 15/03/16 17:00 | 23/12/16 04:00 | WBS Number | 202.46
1 | Group 11 | ALL | 15/03/16 17:00 | 23/12/16 04:00 | WBS Number | 202.46
1.1 | Project Planning and Oversight | ALL | 15/03/16 17:00 | 03/05/16 18:35 | WBS Number | 35.08
1.1.1 | Define Project Structure | ALL | 15/03/16 17:00 | 24/03/16 17:00 | WBS Number | 7
1.1.1.1 | User Stories | ALL | 15/03/16 17:00 | 21/03/16 05:00 | WBS Number | 3.5
1.1.1.2 | Themes/Features | ALL | 15/03/16 17:00 | 21/03/16 05:00 | WBS Number | 3.5
1.1.1.3 | Domain Analysis | ALL | 15/03/16 17:00 | 17/03/16 11:00 | WBS Number | 1.75
1.1.1.4 | Personas | ALL | 15/03/16 17:00 | 24/03/16 17:00 | WBS Number | 7
1.1.2 | Requirements | ALL | 24/03/16 17:00 | 13/04/16 17:00 | 1.1.1 | 14
1.1.2.1 | Software Requirements Analysis | ALL | 24/03/16 17:00 | 13/04/16 17:00 | WBS Number | 14
1.1.2.2 | Preparing Scenarios | ALL | 24/03/16 17:00 | 13/04/16 17:00 | WBS Number | 14
1.1.2.3 | Defining Use-Case Model | ALL | 24/03/16 17:00 | 04/04/16 17:00 | WBS Number | 7
1.1.2.4 | Defining Object Model | ALL | 24/03/16 17:00 | 04/04/16 17:00 | WBS Number | 7
1.1.2.5 | Defining Dynamic Model | ALL | 24/03/16 17:00 | 04/04/16 17:00 | WBS Number | 7
1.1.3 | Design |  | 13/04/16 17:00 | 03/05/16 17:00 | 1.1.2 | 14
1.1.3.1 | Software architecture design |  | 13/04/16 17:00 | 03/05/16 17:00 | WBS Number | 14
1.1.3.2 | Prototyping |  | 13/04/16 17:00 | 03/05/16 17:00 | WBS Number | 14
1.1.3.3 | User Interface |  | 13/04/16 17:00 | 03/05/16 17:00 | WBS Number | 14
1.1.3.4 | Software detailed designSoftware detailed design |  | 13/04/16 17:00 | 03/05/16 17:00 | WBS Number | 14
1.1.4 | Project Examination |  | 15/03/16 18:30 | 15/03/16 18:30 | WBS Number | 0
1.1.5 | Draft of Requirements and Plans |  | 19/03/16 18:32 | 19/03/16 18:32 | WBS Number | 0
1.1.6 | Finalization of Requirements |  | 02/04/16 18:33 | 02/04/16 18:33 | WBS Number | 0
1.1.7 | Mock-ups |  | 16/04/16 18:33 | 16/04/16 18:33 | WBS Number | 0
1.1.8 | Page Functionalities |  | 30/04/16 18:34 | 30/04/16 18:34 | WBS Number | 0
1.1.9 | Planning Finalization |  | 03/05/16 18:35 | 03/05/16 18:35 | WBS Number | 0
1.2 | Implementation |  | 03/05/16 19:00 | 28/09/16 19:00 | 1.1 | 106
1.2.1 | Software Unit Development |  | 03/05/16 19:00 | 08/06/16 19:00 | WBS Number | 26
1.2.1.1 | Android UX Design and Creation |  | 03/05/16 19:00 | 23/05/16 19:00 | WBS Number | 14
1.2.1.2 | Web UX Design and Creation |  | 03/05/16 19:00 | 08/06/16 19:00 | WBS Number | 26
1.2.2 | Backend Software |  | 03/05/16 19:00 | 14/07/16 19:00 | WBS Number | 52
1.2.2.1 | Database Implementation |  | 03/05/16 19:00 | 14/07/16 19:00 | WBS Number | 52
1.2.2.2 | Middleware Development |  | 03/05/16 19:00 | 28/06/16 19:00 | WBS Number | 40
1.2.2.3 | Security Subsystems |  | 03/05/16 19:00 | 14/06/16 19:00 | WBS Number | 30
1.2.2.4 | Search Engine |  | 03/05/16 19:00 | 31/05/16 19:00 | WBS Number | 20
1.2.3 | Graphics and Interface |  | 03/08/16 19:00 | 28/09/16 19:00 | WBS Number | 40
1.2.4 | Content Creation |  | 03/08/16 19:00 | 23/08/16 19:00 | WBS Number | 14
1.2.5 | Software Unit Integration |  | 03/08/16 19:00 | 14/09/16 19:00 | WBS Number | 30
1.3 | Testing |  | 25/08/16 17:00 | 15/12/16 17:00 | WBS Number | 80
1.3.1 | Software Unit Testing |  | 25/08/16 17:00 | 15/12/16 17:00 | WBS Number | 80
1.4 | Release |  | 16/12/16 04:00 | 23/12/16 04:00 | 1.3 | 5